## Sheet1
Order | Category | App Location | Priority | Severity | LOE | Effects | Description | Solution | Image
1 | Bug | Mobile | High | Critical | 8 |  | Login does not work | Mike | No image
2 | Bug | Reaction Dialog | Medium | High | 5 | Mike | Incorrect location displayed | Mike
3 | Bug | All video views | Medium | Medium | 5 |  | Blank videos (Related to 4?) | Mike
4 | Bug | Everywhere | Medium? | Uncertain | 5 |  | Many 404 for videos (Related to 3?) | Mike
5 | Tweak | Tab | Low |  | 1 |  | Fix favicon | Mike
6 | Tweak | Mobile | Low |  |  |  | Menu spacing
7 | Tweak | Camera list in Gallery | Low |  |  |  | Sort order
8 | Tweak | Social Media Icons and Links | Low |  |  |  | Not consistent on pages and reaction dialog
9 | Tweak | Mobile Frontpage | Low |  |  |  | Display does not scroll to bottom of video stack
10 | Tweak | Reaction dialog | Low |  |  |  | Add close button