## Sheet1
Order | Category | App Location | Priority | Severity | LOE | Effects | Description | Solution | Image
1 | Bug | Mobile | High | Critical | 8 |  | Login does not work | Mike | No image
2 | Bug | Reaction Dialog | Medium | High | 5 | Mike | Incorrect location displayed | Mike
3 | Bug | All video views | Medium | Medium | 5 |  | Blank videos (Related to 4?) | Mike
4 | Bug | Everywhere | Medium? | Uncertain | 5 |  | Many 404 for videos (Related to 3?) | Mike
5 | Tweak | Frontpage | High | Low | 3 |  | Forntpage to display highest ranking videos | Fake It? After rename: top three to be 032_20250411T041956937Z.mp4 089_20250411T041955185Z.mp4 132_20250402T18350000Z.mp4 | No image
5 | Tweak | Tab | Low |  | 1 |  | Fix favicon | Mike
6 | Tweak | Mobile | Low |  |  |  | Menu spacing
7 | Tweak | Camera list in Gallery | Low |  |  |  | Sort order
8 | Tweak | Social Media Icons and Links | Low |  |  |  | Not consistent on pages and reaction dialog
9 | Tweak | Mobile Frontpage | Low |  |  |  | Display does not scroll to bottom of video stack
10 | Tweak | Reaction dialog | Low |  |  |  | Add close button
11 | Tweak | Frontpage | Low |  |  |  | Show Likes count and Star icon
12 | Tweak | Everywhere | Low |  |  |  | Make subheadings yellow for contrast
13 | Tweak | Everywhere | Low |  |  |  | Select better images |  | See above
14 | Tweak | Frontpage | Medium |  |  |  | Add instructions to popout on hover or menu |  | No image
15 | Tweak | Frontpage | Low |  |  |  | Change "Top 3 Most Liked Videos" to "Top Videos" |  | No image
16 | Tweak | Frontpage | Low |  |  |  | Display entire page by default | Workaround: F11

## Sheet2
Order | Category | App Location | Priority | Severity | LOE | Effects | Description | Solution
1 | Bug | Mobile | High | Critical | 8 |  | Login does not work | Mike
2 | Bug | Reaction Dialog | Medium | High | 5 | Mike | Incorrect location displayed | Mike
3 | Bug | All video views | Medium | Medium | 5 |  | Blank videos (Related to 4?) | Mike
4 | Bug | Everywhere | Medium? | Uncertain | 5 |  | Many 404 for videos (Related to 3?) | Mike
5 | Tweak | Frontpage | High | Low | 3 |  | Forntpage to display highest ranking videos | Fake It? After rename: top three to be 032_20250411T041956937Z.mp4 089_20250411T041955185Z.mp4 132_20250402T18350000Z.mp4
5 | Tweak | Tab | Low |  | 1 |  | Fix favicon | Mike
6 | Tweak | Mobile | Low |  |  |  | Menu spacing | 0
7 | Tweak | Camera list in Gallery | Low |  |  |  | Sort order | 0
8 | Tweak | Social Media Icons and Links | Low |  |  |  | Not consistent on pages and reaction dialog | 0
9 | Tweak | Mobile Frontpage | Low |  |  |  | Display does not scroll to bottom of video stack | 0
10 | Tweak | Reaction dialog | Low |  |  |  | Add close button | 0
11 | Tweak | Frontpage | Low |  |  |  | Show Likes count and Star icon | 0
12 | Tweak | Everywhere | Low |  |  |  | Make subheadings yellow for contrast | 0
13 | Tweak | Everywhere | Low |  |  |  | Select better images | 0
14 | Tweak | Frontpage | Medium |  |  |  | Add instructions to popout on hover or menu | 0
15 | Tweak | Frontpage | Low |  |  |  | Change "Top 3 Most Liked Videos" to "Top Videos" | 0
16 | Tweak | Frontpage | Low |  |  |  | Display entire page by default | Workaround: F11